## Sheet1
S.No. | Section | Activity | Priorty | Owner | Start Date | Targate date | End Date | Remark
Summary | [8 empty] | Yellow Box :
1 | Data base | Sumarry Template |  | Kuldeep
2 |  | Deasese Type |  | Avinash
3 |  | Device type |  | Avinash
4 |  | Procedure type |  | Avinash
5 |  | Patient Group |  | Avinash
6 |  | Study type |  | Avinash
7 |  | Device Maker |  | Avinash
8 |  | Provide Structure of Database to be created on Django Server |  | Ashwin | 16/5/2020 | 17/05/2020
| Finding Parameters/Factors for Summary | Type of Study |  | Ashwin | 2020-08-03 | 2020-10-04
|  | No. of Patients |  | Ashwin | 2020-08-03 | 2020-10-04
|  | Patient Group |  | Ashwin | 2020-08-03 | 2020-10-04
|  | Procedure type |  | Ashwin | 2020-08-03 | 2020-10-04
|  | Device Maker |  | Ashwin | 2020-08-03 | 2020-10-04
|  | Device type |  | Ashwin | 2020-08-03 | 2020-10-04
|  | Indications |  | Ashwin | 2020-08-03 | 2020-10-04
|  | Mean Age |  | Ashwin | 2020-08-03 | 2020-10-04
|  | First Tool Represented |  | Ashwin | 25/02/2020 | 2020-07-03
| Data Analysis and Visualisation | Analyzing Summaries of 60 Articles and finding useful Parameters |  | Ashwin | 13/04/2020 | 25/04/2020
| Finding Stemmed Values for Database values | Type of Study |  | Ashwin | 13/05/2020 | 18/05/2020
|  | Patient Group |  | Ashwin | 13/05/2020 | 18/05/2020
|  | Procedure type |  | Ashwin | 13/05/2020 | Pending
|  | Device Maker |  | Ashwin | 13/05/2020 | Pending
|  | Device type |  | Ashwin | 13/05/2020 | 18/05/2020
| Insert Stemmed values to Database | Type of Study |  | Ashwin | 13/05/2020 | 19/05/2020 |  | Avinash Sir will coordinate
|  | Patient Group |  | Ashwin | 13/05/2020 | 19/05/2020
|  | Procedure type |  | Ashwin | 13/05/2020 | Pending
|  | Device type |  | Ashwin | 13/05/2020 | 19/05/2020
9 |  | Device Maker |  | Ashwin | 13/05/2020 | Pending
10
| Website Creation | frontend and backend |  | Shashank | 2020-02-05 | 15/05/2020
|  | Database |  | Shashank | 2020-02-05 | 15/05/2020
|  | Deployment to heroku |  | Shashank | 2020-02-05 | 15/05/2020
|  | Integation of NLP Tool |  | Shashank | 2020-02-05 | 15/05/2020
11 | Testing | Need 2 Articles for each type of study for testing purpose |  | Avinash
12 |  |  |  |  | 18/05/2020
13
14
Tools For shortlist article based on criteria
| Website creation | frontend and backend |  | Shashank
|  | website Deployed |  | Shashank
1 |  | Admin panel design |  | Shashank
2 |  | PDF to text | High | Shashank | 18/05/2020
3 |  | Add cache facility to improve website performance |  | Shashank |  |  |  | Rahul will help him
4 |  | Use posibility of additional user | Low | Shashank
5
6
| Implementation | Pubmed API | High | Ashwin | 2020-11-05 | 17/05/2020
|  | Google scholar API |  | Ashwin | 20/05/2020
|  | Embase API |  | Ashwin | 20/05/2020
| Website Integration | Pubmed API | High | Shashank | 20/05/2020 | 25/05/2020
|  | Google scholar API |  | Shashank
|  | Embase API |  | Shashank
The Dates that are enclosed in Yellow Boxes are just assumed dates .
These are not written with surity because the tracker was not present at that time of work , i.e. it was setup later , much after the work was done.